## Assumptions
ID | Assumptions
A.01 | Architecture work is ***usually*** estimated in multiples of 8-hour increments
A.02 | Progression from Low > Med. > High - should NOT be assumed to be a simple linear progression of estimated increase of complexity/effort.
A.03 | As we collect metrics for estimated vs. actual - we will monitor and adjust our estimate ranges. Until then - it may be prudent to add a standard buffer to the estimates (e.g. 20%-25%)

## EA Service Catalog
ID | Category | Service | Low Est. [small] (hours, effort) | Med Est. [med.] (hours, effort) | High Est. [large] (hours, effort) | Expected Artifacts Produced
1 | Consultation Services
1.01 | Consultation Services | Architecture Consultation | 1 | 2 | 4 | Architecture Meeting Notes
1.02 | Consultation Services | Vendor Solution Search/Discovery | 16 | 32 | 64 | Comparison/Summary
1.03 | Consultation Services | Open Source Solution Search/Discovery | 8 | 16 | 32 | Comparison/Summary
1.04 | Consultation Services | RFP Preparation | 24 | 40 | 80 | RFP content, RFP requirements, Selection Criteria
1.05 | Consultation Services | BRD Review | 16 | 32 | 48 | BRD review comments
1.06 | Consultation Services | New Technology Assessment/Opinion Paper | 8 | 16 | 32 | Architecture Guidance, Findings
1.07 | Consultation Services | Performance Trouble-Shooting | 4 | 16 | 32 | Architecture Recommendations, Findings
2 | Proof-of-Concept (PoC)
2.01 | Proof-of-Concept (PoC) | POC design | 24 | 48 | 96 | Architecture Diagrams, Recommendations
2.02 | Proof-of-Concept (PoC) | POC implementation, oversight | 32 | 64 | 128 | Architecture Guidance, Findings
2.03 | Proof-of-Concept (PoC) | POC implementation, lead (hands-on) | 40 | 80 | 160 | Architecture Guidance, Findings
3 | High-Level Design (HLD)
3.01 | High-Level Design (HLD) | HLD, within one domain | 16 | 24 | 48 | SAD/HLD, Architecture Diagrams
3.02 | High-Level Design (HLD) | HLD, across two or more domains | 24 | 48 | 96 | SAD/HLD, Architecture Diagrams
3.03 | High-Level Design (HLD) | HLD, involving one external partner | 24 | 48 | 96 | SAD/HLD, Architecture Diagrams
3.04 | High-Level Design (HLD) | HLD, involving two or more external partner | 24 | 48 | 192 | SAD/HLD, Architecture Diagrams
3.05 | High-Level Design (HLD) | HLD, major system replacment | 24 | 48 | 192 | SAD/HLD, Architecture Diagrams
3.06 | High-Level Design (HLD) | HLD, major new technology introduction | 24 | 48 | 96 | SAD/HLD, Architecture Diagrams
4 | Low-Level Design (LLD)
4.01 | Low-Level Design (LLD) | LLD, within one domain | 24 | 48 | 96 | LLD Guidance/Review, Architecture Diagrams
4.02 | Low-Level Design (LLD) | LLD, across two or more domains | 48 | 96 | 192 | LLD Guidance/Review, Architecture Diagrams
4.03 | Low-Level Design (LLD) | LLD, involving one external partner | 48 | 96 | 192 | LLD Guidance/Review, Architecture Diagrams
4.04 | Low-Level Design (LLD) | LLD, involving two or more external partner | 48 | 96 | 192 | LLD Guidance/Review, Architecture Diagrams
4.05 | Low-Level Design (LLD) | LLD, major system replacment | 48 | 96 | 192 | LLD Guidance/Review, Architecture Diagrams
4.06 | Low-Level Design (LLD) | LLD, major new technology introduction | 48 | 96 | 192 | LLD Guidance/Review, Architecture Diagrams
5 | RFP Support
5.01 | RPF Support | Solution Research - Identify Potential Vendors
5.02 | RPF Support | Evaluate Vendors - Identify Candidates Shortlist
5.03 | RPF Support | Prepare Detailed RFP Evaluation Questions
5.04 | RPF Support | Review Vendor RFP Responses
5.05 | RPF Support | Conduct Hands-on an In-Depth Vendor Evaluation